## Stakeholders
Key stakeholder groups: -Business Analyst (BA) -IT Team (IT) -External Vendor (EV) -Dean of Enrollment (DE) -Enrollement Staff (ES) -Students (S)

## RACI matrix
RACI Matrix | Responsible | Accountable | Consulted | Informed
Requirements Gathering | BA | DE | ES,IT | S | I believe the Business Analyst should be responsible for this task because they need to know all the requirements in order to analyze it and come up with solutions for the requirement. As for the person accountable, I feel the Deand of Enrollment is as they are the person who is in charge of this project so it is his/her job to make sure that BA gathers the correct information. Next, the Enrollment Staff and IT Team should be consulted on the requirements gathering as they will be the two main in-house user of this application. Lastly, the Student Rep should be informed of what the project and how it will benefit it.
System Development | IT,EV | IT, EV | BA | DE | For this task, I feel that the IT Team and External Vendor are both responsible and accountable as the are the SME in this area. I thought about have the Dean of Student being accountable but he/she wouldn't know whether the system was developed correctly or not. I also thought that the EV would be responsible while the IT Team is accountable but I think that the two of them would most likely work together to develop the application. Therefore, the Dean of Student should just be informed of their progress while they consult with the BA on any postive/negative issues they have.
Testing & Feedback | IT, EV | IT, EV | ES, S | DE, BA | I feel that this task is very similar to the previous one with only changes to who are being consulted. The IT Team and External Vendors will again both be responsible and accountable for making any changes to the system after consulting with the Enrollment Staffs and the Student Rep about what works well and what doesn't. After these testing, the Dean of Enrollment and Business Analyst should be informed of this to make decisions so that the project falls within the timeline.
Training of staff | IT | DE | ES | BA | Once the new system is up and ready to go, the Dean of Enrollment should oversea and make sure the the Enrollent Staffs are trained by the IT Team while the ES are also giving feedbacks on how well the trainings are going. The Business Analyst should be informed of how well the project is coming along.
Deployment | IT, EV | DE | BA | ES,S | Lastly, during the deployment stage of this project, the IT Team and the External Vendors should both be responsible for carry this out while the Dean of Student is accountable for making sure this process is done smoothly. Also, the Business Analyst should be consulted prior to deployment to make sure all of the requirements are met. After deployment, make sure to inform the Enrollment Staffs and the Students of this change so that everyone is aware of it.
Key stakeholder groups: -Business Analyst (BA) -IT Team (IT) -External Vendor (EV) -Dean of Enrollment (DE) -Enrollement Staff (ES) -Students (S)

## Personas & Engagement Plans
Personas
Persona 1 | IT Team Member (Sarah)
Role | Lead Developer
Demographics & Experience | 32 years old, held current position for 3 years
Expertise | Expert level experience in system integration
Goals | Deliver a functional, bug-free system within the timeline.
Concerns | How accurate the data will be when migrating from the previous system as well as having proper firwalls to prevent security breaches.
Preferred Communication | Emails, and weekly meetings- because as an IT member, she'll mainly be on her computer/laptop thus making emails the fastest way to reach her. As the lead developer on this project, having weekly meetings with her will also help communicate any feedbacks or changes to the requirements so that everyone is updated on them.
Persona 2 | Enrollment Staff Member (James)
Role | Administrative Assistant
Demographics & Experience | 45 years old, 10 years in the enrollment office.
Expertise | Following procedures to a "T"
Goals | To have the new system up and ready to go in a timely matter so that he can learn it quickly in order to process student applications with minor setbacks.
Concerns | Features that worked well in the old system may be replaced with new ones that will require additional training.
Preferred Communication | As an AA for 10 years and still pretty young at 45, he should be fine with any kind of communications from emails, to phone call, to chats, or meetings.
Persona 3 | Student Representative (Maria)
Role | Junior at the college
Demographics & Experience | 20 years old, studies Business Administration.
Expertise | Transferred from two other institutions, large friend group
Goals | Wants the new system to be easy to use and accessible across many devices while protecting their data privacy
Concerns | Any system downtime will affect students' ability to enroll and select courses/time slots
Preferred Communication | Emails, texts, or online chats.
Engagement Plan | Match each with the options on "Matching Choices" sheet
1. Dean of Enrollment Services
Strategy | Weekly briefings to review progress and seek approvals. Include them in milestone meetings.
Resistance Mitigation | Provide cost-benefit analysis and emphasize alignment with institutional goals.
2. IT Team
Strategy | Daily stand-ups for developers, detailed project schedules, and collaborative issue tracking (e.g., Jira).
Resistance Mitigation | Allocate time for technical challenges and foster open communication about resource needs.
3. Enrollment Staff
Strategy | Conduct focus groups to gather requirements, provide training early, and collect feedback during testing.
Resistance Mitigation | Emphasize time savings and reduced workload. Offer support during and after launch.
4. Student Representative
Strategy | Regular feedback sessions to test prototypes and improve usability. Include a student survey to gather wider opinions.
Resistance Mitigation | Highlight improvements to the student experience, like shorter enrollment times and better communication.
5. External Vendor
Strategy | Clear technical requirements and regular check-ins to monitor progress. Ensure their deliverables align with internal timelines.
Resistance Mitigation | Create penalties for delays and incentives for on-time delivery.

## Matching Choices
Strategies for collaboration
Weekly briefings to review progress and seek approvals. Include them in milestone meetings.
Daily stand-ups for developers, detailed project schedules, and collaborative issue tracking (e.g., Jira).
Conduct focus groups to gather requirements, provide training early, and collect feedback during testing.
Regular feedback sessions to test prototypes and improve usability. Include a student survey to gather wider opinions.
Clear technical requirements and regular check-ins to monitor progress. Ensure their deliverables align with internal timelines.
Resistance Mitigation Techniques
Provide cost-benefit analysis and emphasize alignment with institutional goals.
Allocate time for technical challenges and foster open communication about resource needs.
Emphasize time savings and reduced workload. Offer support during and after launch.
Highlight improvements to the student experience, like shorter enrollment times and better communication.
Create penalties for delays and incentives for on-time delivery.

## Justification
Purpose of RACI:
A RACI matrix is primarily a tool of the project manager who uses it as the beginning of the project or phase to make sure all "bases" are covered and everyone is on the same page when it comes to duties and responsibilities. It can help alleviate team miscommunication and bottlenecks when it comes to work and approvals.
Purpose of stakeholder matrices and personas (from BABOK):
Stakeholder lists, maps, and personas assist the business analyst in analyzing
stakeholders and their characteristics. This analysis is important in ensuring that
the business analyst identifies all possible sources of requirements and that the
stakeholder is fully understood so decisions made regarding stakeholder
engagement, collaboration, and communication are the best choices for the
stakeholder and for the success of the initiative.